## Tasks
TASKS
Task ID | Task Name | Assigned To | Start Date | End Date | Duration | Status | % Complete | Progress | Notes
1 | Market Research | Research Team | 2050-06-01 | 2050-06-14 | 14 DAYS | Completed | 100% |  | Initial market analysis completed
2 | Product Conceptualization | Product Team | 2050-06-15 | 2050-07-05 | 21 DAYS | Ongoing | 60% |  | Concept art in review
3 | Feasibility Study | Analysis Team | 2050-06-10 | 2050-07-10 | 31 DAYS | Ongoing | 50% |  | Awaiting final risk assessment
4 | Financial Planning | Finance Department | 2050-07-11 | 2050-08-01 | 22 DAYS | Not Started | 0% |  | To begin after feasibility approval
5 | Prototype Development | Engineering Team | 2050-08-02 | 2050-09-15 | 45 DAYS | Not Started | 0% |  | Materials being sourced
6 | Branding & Identity Creation | Marketing Department | 2050-07-06 | 2050-08-10 | 36 DAYS | Ongoing | 30% |  | Logo finalized, color scheme in dev
7 | Testing Phase I | QA Team | 2050-09-16 | 2050-10-16 | 31 DAYS | Upcoming | 0% |  | Scheduled after prototype dev
8 | Marketing Strategy | Marketing Department | 2050-10-01 | 2050-11-01 | 32 DAYS | Upcoming | 0% |  | Awaiting market research update
9 | Compliance Checks | Legal Team | 2050-09-01 | 2050-10-05 | 35 DAYS | Upcoming | 0% |  | Dependencies on final product specs
10 | Launch Event Planning | Events Team | 2050-11-02 | 2050-11-25 | 24 DAYS | Upcoming | 0% |  | Venue to be booked by 2050-10-01
CHOOSE & DOWNLOAD MORE TIMELINE TEMPLATES |  |  |  | © TEMPLATE.NET
Note on B2: Simply select an entire row and drag down to add more tasks.
Note on G6: Auto Formulated

## Gantt Chart
GANTT CHART
[8 empty] | 💡 | THE CALENDAR SECTION OF THE GANTT CHART IS AUTO FORMULATED. NO NEED TO EDIT.
 | time axis 2050-06-01 to 2051-05-21
TASK | ASSIGNED TO | START TIME | END TIME | STATUS | % COMPLETE | PROGRESS | DURATION (days)
0
Market Research | Research Team | 2050-06-01 | 2050-06-14 | COMPLETED | 100% | 1 | 13
Product Conceptualization | Product Team | 2050-06-15 | 2050-07-05 | IN PROGRESS | 80% | 0.8 | 20
Feasibility Study | Analysis Team | 2050-06-10 | 2050-07-10 | IN PROGRESS | 43% | 0.43 | 30
Financial Planning | Finance Department | 2050-07-11 | 2050-08-01 | IN PROGRESS |  |  | 21
Prototype Development | Engineering Team | 2050-08-02 | 2050-09-15 |  |  |  | 44
Branding & Identity Creation | Marketing Department | 2050-07-06 | 2050-08-10 |  |  |  | 35
Testing Phase I | QA Team | 2050-09-16 | 2050-10-16 |  |  |  | 30
Marketing Strategy | Marketing Department | 2050-10-01 | 2050-11-01 |  |  |  | 31
Compliance Checks | Legal Team | 2050-09-01 | 2050-10-05 |  |  |  | 34
Launch Event Planning | Events Team | 2050-11-02 | 2050-11-25 |  |  |  | 23
Note on H10: PROGRESS BAR IS AUTOMATED BASED ON THE % COMPLETED COLOUMN
Note on I10: DURATION IS AUTO FORMULATED BASED ON START AND END DATE