## Marketing Project Management
MARKETING PROJECT MANAGEMENT
PROJECT DETAILS
Project Name | Product X Launch
Project Manager | Mark Johnson
Start Date | 2023-10-15
End Date | 2023-11-30
Total Budget | 50000
Client | XYZ Corporation
TASK LIST |  |  |  |  | BUDGET ALLOCATION |  | RESOURCE ALLOCATION
Assigned To | Task Description | Start Date | End Date | Status | Category | Budget Allocation ($) | Resource | Role
Marketing | Market Research & Analysis | 2023-10-15 | 2023-10-31 | In Progress | Market Research | 5000 | John Doe | Project Manager
Marketing | Develop Marketing Strategy | 2023-11-01 | 2023-11-10 | Not Started | Marketing Strategy | 10000 | Alice Smith | Designer
Design | Design Creative Assets | 2023-11-05 | 2023-11-20 | Not Started | Design & Creative | 8000 | Mark Johnson | Web Developer
Content | Content Creation | 2023-11-10 | 2023-11-25 | Not Started | Content Creation | 6000 | Sarah Brown | Content Writer
Web Dev | Website Development | 2023-11-15 | 2023-11-30 | Not Started | Web Development | 7000 | Laura White | Social Media Manager
Social Media | Social Media Campaign | 2023-11-20 | 2023-11-30 | Not Started | Social Media | 5000 | Chris Davis | PR Specialist
Marketing | Email Marketing | 2023-11-15 | 2023-11-28 | Not Started | Email Marketing | 6000
PR | PR & Media Relations | 2023-11-25 | 2023-11-30 | Not Started | PR & Media Relations | 3000
QA | Quality Assurance & Testing | 2023-11-28 | 2023-11-30 | Not Started | Contingency | 10000
[5 empty] | TOTAL | 60000

## Setup
SETUP
Assigned To | Category | Resource | Role
Marketing | Market Research | John Doe | Project Manager
Design | Marketing Strategy | Alice Smith | Designer
Content | Design & Creative | Mark Johnson | Web Developer
Web Dev | Content Creation | Sarah Brown | Content Writer
Social Media | Web Development | Laura White | Social Media Manager
Marketing | Social Media | Chris Davis | PR Specialist
PR | Email Marketing
QA | PR & Media Relations
Contingency

## Instructions
https://docs.google.com/spreadsheets/d/1fJtCMvXoigfc9dWaKu-HKbVSBFIkUt4-pysPxmCw8Sg/edit#gid=2113230748
The following are instructions on how to use the template.
1. Edit or add content like inserting rows and columns to the template.
2. There are no locked-up cells for easier editing of cell names.
3. Feel free to change any formula available.
Should you need assistance, please contact our Customer Support Team using the chat box found on the website.